## Meetings Needed
Risks
| Who are all the stakeholders? | Data Engineering (ETL) Dev, QA, ?????
Agree on template of end deliverables (with USAA?)
Need help with kicking off meeting with DPO & MFP teams
|  |  |  | Sprint 1 |  | Sprint 2 |  | Sprint 3
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Follow ups | Topic | Meeting Agenda | Data Modernization Teams | Aug 11th Aug 18th | Aug 19th Aug 25th | Aug 26th Sep 1st | Sep 2nd Sep 8th | Sep 9th Sep 15th | Sep 16th Sep 22nd | Touchpoints for updates (3 times a week)
| Discovery (Dev) | Initial Data gathering | Data Engineering (ETL) Team | Aug 11th
| Discovery (QA) | Initial Data gathering | QA team | Aug 11th
| Discovery (DPO) | Session 1 - * Identify all stakeholders. * Review reqs intake process and the end to end timeline mapping of project execution. * Review the PI metrics which defines the problem of project velocity from a PMO perspective. * Share Dev and QA Reqs related feedback | PMO, Business Analyst & SME | Aug 17th | [5 empty] | x
|  | Session 2 - Follow for clarifications | PMO, Business Analyst & SME |  | Aug 20th
Y | Discovery (MFP) | Session 1 - Initial data gathering * MFP Component Inventory * Catalog of all processes/use cases * Challenges by Process. | MFP Core team | Aug 17th | [5 empty] | x
|  | Session 2 -Review by use cases and gather metrics | MFP Core team | Aug 18th | [5 empty] | x
|  | Session 3 -Review by use cases and gather metrics | MFP Core team |  | Aug 19th
|  | Session 4 -Review by use cases and gather metrics | MFP Core team |  | Aug 23rd
|  | Session 5 - Discuss possible approach to operational improvements | MFP Core team |  |  | Aug 25th |  |  |  | x
|  | Session 6 - Discuss possible approach to operational improvements |  |  |  |  | Sep 1st
|  | Session 7 -Team concesus building on recommendations | MFP Core team |  |  |  |  | Sep 8th |  | x
| Environments (Conflicts and delays due to Dev & QA sharing a common test environment. Agile testing is not happening due to environment sharing, and attributes availability in test environment. ( Additional E2E preparation time causing stabilization (end to end testing and UAT testing ) delays.) | Session 1 * Tools & Technologies & Ownership * Review current issue of environment conflict with QA * Review unit test approach & DVF * Review versioning & code promotion process | Data Engineering (ETL) Team | Aug 16th | [5 empty] | x
|  | Session 2 Map all environments in Data pipeline Document issues across all apps in pipeline | All Pipeline teams | Aug 18th
|  | Session 3 Review constraints and potential solution options | Data Engineering (ETL) Team |  | Aug 20th |  |  |  |  | x
|  | Session 4 Review constraints and potential solution options | All Pipeline teams |  | Aug 23rd
|  | Session 5 Impementation planning session | All Pipeline teams |  |  | Aug 26th
|  | Session 6 Impementation planning session (follow up) | All Pipeline teams |  |  | Aug 31st
|  | Session 7 Consolidated review of output from Sessions | All Pipeline teams |  |  |  | Sep 3rd |  |  | x
Y | Requirements Management (Dev and QA invests a lot time in requirements analysis which increases development cycle times. IT is getting the requirements from the legacy code, and the same information is provided as the requirements for testing. No business ownership on the requirements) | Session 1 - * A clearer understanding of the problem. * Review the requirements analysis process & ownerships * Use of Jira * Team next steps. | PMO, Data Engineering (ETL) Team, SME's, QA | Aug 17th | [5 empty] | x
|  | Session 2 - Clarifications followups | PMO,Data Engineering (ETL) Team, SME's, QA | Aug 18th
|  | Session 3 - Team recommendations discussions. | PMO, Data Engineering (ETL) Team, SME's, QA |  | Aug 20th |  |  |  |  | x
|  | Session 4 - Team recommendations discussions (follow up) | PMO, Data Engineering (ETL) Team, SME's, QA |  | Aug 24th
|  | Session 5 - Consesus on recommendations & execution approach discussion. | PMO,Data Engineering (ETL) Team, SME's, QA |  |  | Aug 26th
|  | Session 6 - Final review of recommendations & execution approach | PMO, Data Engineering (ETL) Team, SME's, QA |  |  |  | Sep 8th
| Requirements Management (Miscommunications between Dev & QA on requirements leading to poor test coverage and longer development cycle times) | Session 1 - * Deeper dive into the issues | Data Engineering (ETL) Team, QA | Aug 17th | [5 empty] | x
|  | Session 2 - Refinement of recommendations (Might be covered under end to end requirements management) | PMO, Dev & QA | [6 empty] | x
| Testing (QA has experienced delays due to regression testing defects and ETL Dev has acknowledged lack of unit test coverage) | Session 1 - Follow up clarifications | QA | Aug 16th | [5 empty] | x
|  | Session 2 - Joint meeting with Dev & QA * Review issues with requirements communication * Review testing concerns | ETL Dev Team, QA | Aug 17th
|  | Session 3 - Review current state end to end testing strategy and test data preparation approach | All Pipeline teams |  | Aug 19th
|  | Session 4 - Followup clarifications & next steps discussion | All Pipeline teams |  | Aug 24th
|  | Session 5 - Draft recommendations | All Pipeline teams |  |  | Aug 26th
|  | Session 6 - Review recommendations & execution planning | All Pipeline teams |  |  | Aug 30th
|  | Session 7 - Finalize recommendations & execution planning | All Pipeline teams |  |  |  | Sep 8th
| IT Process & End to End Release Management (Dev has highlighted Governance processes like DBA approvals, production move change review processes are in critical path of delivery and impact dev timelines.) | Session 1 * List of all processes ETL Dev teams participate * Painpoints & impact by process | Data Engineering (ETL) Team
|  | Session 2 * Broader review of process catalog * End to End release management process * Define next steps | ???
Session 3 * Place holders
Session 4 * Place holders
Session 5 * Draft recommendations & execution plan
Session 6 * Finalize recommendations & execution plan
| Informatica Migration (Review Branching, Merging, deployment strategies, upstream and downstream dependencies - current state and challenges) | Session 1 (Is there a need to make a case for DBT) * |  |  | Aug 19th
Placeholder for MFP Findings
| Review of findings with Leadership & Stakeholders |  |  |  |  | x | x | x
Brian bi-weekly cadence
Note on A19: Shiby Surendranath: Check with Suresh
Note on A35: Shiby Surendranath: Request Suresh to schedule
Note on E42: Shiby Surendranath: Combined with Dev & QA testing meeting on Aug 17th
Note on F47: Shiby Surendranath: Conduct after the intial Environment meeting
Note on H51: Shiby Surendranath: Firm up environments before finalizing this