## Action Items tracker
Recorded On | Topic | Query | Pending with | Status | Comments
2021-08-11 | Requirements | In the "Claims New Work Intake Process" please provide a) Cycle times per activity. Provide a rough estimate of the avg cycle time and the worst case cycle times. b) For each activity provide pain points. | Rob Newman | Open | 8/13 Shiby - Provide what is known to dev and the rest can be requested from the other participants

## Dev & QA Brainstorming
QA - Request to move DVF untility off Informatica Servers (will impact QA's ability to run regression tests)
No consistency with the number of environments across systems |  | Control+M??
QA receiving incomplete requirements from dev (results in poor test coverage and rework resulting in longer testing cycles) |  | Xray ????
Test environment shared by Dev & QA (causing conflicts, bottlenecks) |  | qTest is cumbersome to use
Insufficient requirements - Dev time in requirements analysis | QA Team - Lack of domain knowledge in the team to create test cases | Informatica Limitations (with parallel releases, unit testing, versioning)
Materials (Availability of data, requirements, architecture or design guidance) | People (Missing skillsets, Resource availability, too many resources…...) | Machines (Software or Hardware in use affecting producitivity)
High Dev Cycle Times
Methods/Procedures/Policies (Contributing to the problem) | Measures/Metrics (Any concerns with how metrics are computed) | Work Environment (People interactions or physcical facilities)
Dev unit testing processes (Dev - There is no consistency in unit testing and lot of the testing is manual)
Regression Testing process ( does not capture defects from earlier code drops)
DBA Approval Process (DDL Deployment taking too long)
CAB Process (Delays dev releases)
Code promotion process (QA - need code changes to promote between environments)
QA and Dev tracks users stories in separate repositories (poor traceability, test coverage and increased testing cycles)
QA - Test data preparation process
Dev - dev test environment setup taking too long
DPO - Delays in Claims New Work Intake Process
Note on C12: Shiby Surendranath: Xray is great in that we can use the dependencies we need, but it is overzealous in blocking out huge trees of dependencies we have to go and spend hours reconciling [Provided by Suresh via Slack]
Note on A13: Shiby Surendranath: Local development wise developers have no way to reliable test our applocations to match the OCP environment with Security. [Provided by Suresh via Slack]
Note on C13: Shiby Surendranath: Qtest has added extra hours of work to testing with an unintutive interface and lack of reliable automation on Gitlab pipeline and legacy automation [Provided by Suresh via Slack]
Note on A20: Shiby Surendranath: DBA review of DDL scripts before commencement of development. The DBA rarely reject any request and do not provide any input on improving data model. DB teams sometime takes months to fullfill DB creations which require tones of requests, escalations and followups using multiple contacts [Provided by Suresh via Slack]
Note on A25: Shiby Surendranath: Gitlab pipeline infrastructure takes long periods of time to deploy applications because of how slow the runners are, giving developers huge cycle times to test things in the TOCP environment. [Provided by Suresh via Slack]
Note on A27: Shiby Surendranath: Need to analyze process to confirm

## Deep Dive
General Questions |  | Comments | Freq | Latency | Relative Priority | Team recommendations
What is the duration of Sprint
Materials (Availability of data, requirements, architecture or design guidance)
Insufficient requirements - Dev time in requirements analysis
Why?
Why?
Why?
Why?
Why?
Test environment shared by Dev & QA (causing conflicts, bottlenecks)
Why?
Why?
Why?
Why?
Why?
QA receiving incomplete requirements from dev (results in poor test coverage and longer testing cycles)
Why?
Why?
Why?
Why?
Why?
No consistency with the number of environments across systems
Describe the issue in terms of dev delays
QA - Request to move DVF untility off Informatica Servers (will impact QA's ability to run regression tests)
Describe the issue in terms of dev delays
Methods/Procedures/Policies
Dev unit testing processes (Dev - There is no consistency in unit testing and lot of the testing is manual)
What are the dev practices in place to minimize code issue prior to release to QA?
How does Dev prepare/source test data for its testing?
What are the constraints for unit testing in Dev?
What level of testing is done by dev to ensure that new changes do not break existing functionality?
What is the feasibility of using DVF for automation testing? What are the limitations or concerns with using it.
How are user stories and defects tracked during development?
Regression Testing process ( does not capture defects from earlier code drops)
Why?
Why?
Why?
Why?
Why?
DBA Approval Process (DDL Deployment taking too long)
Why?
Why?
Why?
Why?
Why?
CAB Process (Delays dev releases) - (Is this a single issue more multiple)
Why?
Why?
Why?
Why?
Why?
Code promotion process (need code changes to promote between environments)
Describe the activities involved in promotion code from Dev thru QA to Production?
Is there a planned release schedule to QA? How many releases are done per week?
Why?
Why?
Why?
Why?
Why?
QA and Dev tracks users stories in separate repositories (poor test coverage and increased testing cycles)
Why?
Why?
Why?
Why?
Why?
QA - Test data preparation process
Explain this in terms of impact to dev cycle times
Dev - dev test environment setup taking too long
DPO - Delays in Claims New Work Intake Process
Machines (Software or Hardware in use affecting producitivity)
Informatica Limitations (with parallel releases, unit testing, versioning) - Explain how it impacts dev times
Versioning?
unit testing?
parallel release?
qTest is cumbersome to use
why?
why?
why?
why?
why?
Xray ????
why?
why?
why?
why?
why?
Control+M??
why?
why?
why?
why?
why?
People (Missing skillsets, Resource availability, too many resources…...)
QA Team - Lack of domain knowledge in the team to create test cases
Describe how this affect dev timelines?
Measures/Metrics (Any concerns with how metrics are computed)
Work Environment (People interactions or physcical facilities)
Other questions
Time invested in production support?
Follow up questions
Requirements intake process
Contacts
MFP Team contacts
DPO Team contacts
Note on D1: Shiby Surendranath: High (H) - happens every release. Med (M) - happens often enough to be frustrating. Low (L) - Happens occassionaly but not significant impact
Note on E1: Shiby Surendranath: High (H) - when it happens is always significantly impact project schedules. Med (M) - impact project schedules but can workaround it. Low (L) - no impact to schedule but is frustrating to deal with.
Note on F1: Shiby Surendranath: 10 - High 1 - Low
Note on A13: Shiby Surendranath: Local development wise developers have no way to reliable test our applocations to match the OCP environment with Security. [Provided by Suresh via Slack]
Note on A57: Shiby Surendranath: DBA review of DDL scripts before commencement of development. The DBA rarely reject any request and do not provide any input on improving data model. DB teams sometime takes months to fullfill DB creations which require tones of requests, escalations and followups using multiple contacts [Provided by Suresh via Slack]
Note on A92: Shiby Surendranath: Gitlab pipeline infrastructure takes long periods of time to deploy applications because of how slow the runners are, giving developers huge cycle times to test things in the TOCP environment. [Provided by Suresh via Slack]
Note on A96: Shiby Surendranath: Need to analyze process to confirm
Note on A110: Shiby Surendranath: Qtest has added extra hours of work to testing with an unintutive interface and lack of reliable automation on Gitlab pipeline and legacy automation [Provided by Suresh via Slack]
Note on A118: Shiby Surendranath: Xray is great in that we can use the dependencies we need, but it is overzealous in blocking out huge trees of dependencies we have to go and spend hours reconciling [Provided by Suresh via Slack]